## Active Jobs
JobNo | Client | Town | Type | Status | StartDate | KeyDate | Contract | Received | Balance
CCW-2025-11 | T. Marsh | Craftsbury | Built-in shelves | Complete | 2025-11-12 | Installed 2026-01-20 | 6800 | 6800 | 0
CCW-2026-03 | Henderson | Stowe | Cherry kitchen | In progress | 2026-01-12 | Install 2026-12-08 | 24500 | 9800 | 14700
CCW-2027-01 | Hollister | Greensboro | Barn frame | Quoting | pending | Target summer 2027 | 0 | 0 | 0

## Notes
Job | Note
CCW-2025-11 | Paid in full. Photos sent to Keith for website.
CCW-2026-03 | Lumber bought 2026-02-06. Build through fall. Confirm install week by late Nov.
CCW-2027-01 | Waiting on roofer timing before pricing hemlock sills.